## Overview
Ensyncro — execution plan
4 days x 6 hours — single production environment (demo/staging deferred, see Prompts_Summary). Production hardening tracked separately (see 'Phase 2' sheet).
Day | Focus | Key outputs | Status
Day 1 | Foundations | Monorepo scaffold, Angular + NestJS + Postgres wired, git repo pushed, auth skeleton (signup/login/OTP mock) | Done
Day 2 | Core roles & data model | Founder + Investor onboarding wizards, RBAC guards, admin invite-only bootstrap, DB schema migrated | In progress
Day 3 | Marketplace features | Discover pages (filters), data room with signed-URL file access, CMS content editor + Excel upload | Not started
Day 4 | Polish + staging deploy | Homepage live-stat wiring, color palette applied, production deploy verified, demo-mode logins, QA pass | Not started

## Task tracker
Task tracker
Update Status as we go. Owner defaults to Claude Code unless noted.
# | Day | Task | Area | Owner | Status
1 | Day 1 | Init git repo, connect to GitHub remote | Infra | Claude Code | Done
2 | Day 1 | Scaffold Angular frontend app | Frontend | Claude Code | Done
3 | Day 1 | Scaffold NestJS backend + Postgres connection | Backend | Claude Code | Done
4 | Day 1 | Env config for production (single environment — demo/staging deferred) | Infra | Claude Code | Done
5 | Day 1 | Auth: signup, login, JWT, mock OTP | Backend | Claude Code | Done
6 | Day 2 | RBAC guards for Admin / Founder / Investor | Backend | Claude Code | Not started
7 | Day 2 | Founder onboarding wizard (company profile) | Frontend | Claude Code | Not started
8 | Day 2 | Investor onboarding wizard (incl. investor type) | Frontend | Claude Code | Not started
9 | Day 2 | Admin bootstrap script + invite-only admin creation | Backend | Claude Code | Not started
10 | Day 2 | Core DB schema migration (auth-slice done; remaining PRD sec.7 tables land with their features) | Database | Claude Code | In progress
11 | Day 3 | Discover Founders / Discover Investors pages + filters | Frontend | Claude Code | Not started
12 | Day 3 | Data room: private storage + signed-URL file serving | Backend | Claude Code | Not started
13 | Day 3 | Data room access audit log | Backend | Claude Code | Not started
14 | Day 3 | Admin CMS: editable homepage copy + pricing tiers | Backend | Claude Code | Not started
15 | Day 3 | CMS bulk edit via Excel upload | Backend | Claude Code | Not started
16 | Day 4 | Homepage live stats wired to platform_stats table | Frontend | Claude Code | Not started
17 | Day 4 | Apply chosen color palette across app | Frontend | Claude Code | Not started
18 | Day 4 | Demo-mode one-click logins for all 3 roles | Frontend | Claude Code | Not started
19 | Day 4 | Connect GitHub repo to Vercel for auto-deploy | Infra | You (one-time, dashboard) | Done
20 | Day 4 | Production QA pass + pull screenshots for pitch deck | QA | You + Claude (chat) | Not started

## Phase 2 (production)
Phase 2 — production hardening
Not scoped into the 4-day build. Track separately once production is stable and validated.
Item | Why it matters | Status
Real OTP/SMS provider integration | Demo/staging uses mock OTP — production needs a real provider (Twilio, MSG91, etc.) | Not started
Security review / penetration test | Funding platform handles sensitive founder/investor data | Not started
Legal review — SEBI / securities solicitation rules (India) | Funding-matching platforms can brush up against solicitation regulations | Not started
Payment/escrow integration | Out of scope for phase 1 discovery/data-room MVP | Not started
Native push notifications | Nice-to-have, not core to MVP validation | Not started